## Sheet1
Approved on 05.06.2024
Goal | Action | Task | Owner | Status | Anticipated date | Priority | Timeline | Notes
BUILDING AN UNITED COMMUNITY | We will celebrate the growing diversity of our communities by ensuring that everyone is consulted and represented and we will work to connect neighborhoods together.
|  | Complete Strategy consultation and take account of comments received in writing final Strategy document. | Clerk | Done | 2024-04-15 | High | 01/03/2024 to 16/04/2024
|  | Consult on major new projects where expenditure is above 25% of Precept | Clerk | As needed | 2025-06-01 | TBC
|  | -Continue to celebrate successes in the community or by individuals 4 times per year. | CM | Working on it | 2025-06-01 | Medium | 01/01/2024 to 01/01/2025
|  | -Continue to provide at least one new public bench during year, continue “Donate a bench” scheme but review in March. | Clerk | Working on it | 2025-06-01 | Low | 01/06/2025 to 01/06/2025
We will actively engage with and support a wide range of community organisations that help us achieve our goals and continue to provide funding.
|  | Revise Micro and Small Grant Scheme and Donations Policy to ensure they align with new Strategy. | Clerk | Not started yet | 2024-07-14 | Medium
|  | -Continue to support community and voluntary groups through the Grant Scheme. | CM | Working on it | 2025-03-31 | Medium
|  | -Host at least 2 events which bring together community and voluntary groups and identify how the Parish Council can best support them collectively and how they can support each other. | CM | Not started yet | 2025-03-31 | Medium
|  | -Publicise community and voluntary groups through all Parish Council channels, and promote the concept of volunteering and the opportunity to join specific groups. | CM | Working on it | 2025-03-31 | Medium |  | Wellbeing Wednesday, Newsletter
We will collaborate with partners and service providers, and hold them accountable when necessary. We'll also coordinate with stakeholders to develop a shared plan for improving local services
|  | -Respond to consultations by service providers to ensure the community views are fully articulated. | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing via Planning Committee mainly
|  | Engage with both voluntary and statutory service and facility providers to understand how local services might be improved or supplemented. | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing
|  | We will support residents' campaigns for better broadband | Clerk | As needed | 2025-06-01 | TBC
|  | We will lobby stakeholders to improve the mobile signal in the Parish | Clerk | As needed | 2025-06-01 | TBC
We will implement our Neighbourhood Plan, ensuring it stays relevant, and advocate effectively for our parish in planning decisions.
|  | Use on going planning observations to ensure NP policies are being enforced. | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing via Planning Committee mainly
|  | Liaise with community partners to identify any NP policies which are not progressing | Clerk | As needed | 2025-06-01 | TBC |  | Ongoing via Planning Committee mainly
|  | Complete a mid-term review of the Neighbourhood Plan with community partners. | Clerk | Working on it | 2025-12-31 | Medium
|  | Agree programme, and commence development on a new Neighbourhood Plan. | Clerk | Not started yet | 2030-01-01 | Low
We will advocate for balanced development in our community, ensuring a variety of housing options that meet the diverse needs of our residents throughout their lives. We will work to prevent excessive development in the Parish.
|  | We will review planning applications fairly and objectively, casting a critical eye over proposals and applying the Neighbourhood Plan, Local, and National policies in order to form a balanced view on behalf of the Parish | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing via Planning Committee mainly
We will also advocate for sufficient infrastructure and social services to support our community's growth and development.
|  | Lobby through planning for increased infrastructure to meet the need generated by development or for a contribution from developers. | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing via Planning Committee mainly
|  | Lobby statutory providers for increased provision when a need can be justified. | Clerk | As needed | 2025-06-01 | TBC |  | Ongoing via Planning Committee mainly
|  | We will engage with the Local Authority regarding s.106/CIL matters to optimise community benefits within the Parish | Clerk | Not started yet | 2030-01-01 | Low
We will make an effort to connect with the younger generation and meet their needs within the parish. We will ensure they have opportunities to aspire to and engage with the community.
|  | Liaise with schools and ensure local government is understood. | CM | Working on it | 2025-06-01 | Medium |  | Workshops at the school re- IMPACT and D-Day Program. + Councillors invited at school for International day
|  | Support a school parliament and make part of the small grant budget available to projects of their choice. | CM | Not started yet | 2025-06-01 | Medium
|  | Support youth organisations within the Parish | CM | Not started yet | 2025-06-01 | TBC
|  | Seek external funding opportunities to deliver activity workshops for under 18s | CM | Working on it | 2025-06-01 | Medium |  | Application for Shakedown Wednesday unsuccessful. But D-Day programme included filming and creative writing workshops for Shavington Academy
|  | Develop our digital strategy to ensure better social media communication with the under 25s. | Comms Off | Not started yet | 2025-06-01 | Medium
We will make sure to keep promoting and organising high-quality events with partners that bring our community together and strengthen our bonds, or highlight the Parish. We will ensure that we actively participate in community events and initiatives to support and enhance our parish.
|  | Support events which bring our communities together through the Grants Scheme. | CM | Working on it | 2025-06-01 | Medium |  | £250 to Shavington Village Festival
|  | Lead on Christmas Carol service function for the Parish. | CM | Working on it | 2025-06-01 | High
|  | Promote other community events through all Council channels. | Comms Off | Not started yet | 2025-06-01 | High
|  | We will implement the “Honorary Freemen/ Honorary Freewomen” scheme | Clerk | Working on it | 2025-06-01 | Low |  | Policy in place
|  | We will introduce a “Community Hero” award scheme | Clerk - Comms Off | Not started yet | 2025-06-01 | Low
We will stay vigilant about any concerns regarding the potential loss of community assets, and provide assistance whenever possible.
|  | Ongoing | Clerk | As needed | 2025-06-01 | TBC
We will ensure that the public can participate in Council and committee meetings.
|  | Continue to hold a public participation session at all public meetings. | Clerk | Completed | 2025-06-01 | High |  | All meeting to be held downstairs
CELEBRATING OUR HERITAGE
We will actively support significant public and civic events with historical importance.
|  | D-Day Remembrance Service and programme | CM | Working on it | 2024-11-10 | High
|  | Other National days of importance | CM | Working on it | 2024-06-08 | High |  | D-day program
We will make sure the history of Shavington-cum-Gresty is documented and available for everyone to access.
|  | Include an historical article in each Quarterly Newsletter | CM | Working on it | 2025-06-01 | Medium |  | One historical article in each newsletter
|  | D-Day Commemorative booklet | CM | Completed | 2025-06-08 | Medium
|  | Contact organisations active in the Parish to understand the proposed or ongoing schemes and information available. | CM | Working on it | 2025-06-01 | Medium
|  | Create a History and Heritage section online and gradually populate it. | Comms Off | Not started yet | 2025-06-01 | Low
|  | Appeal to community for historical facts, photographs or anecdotes about the Parish | Comms Off | Not started yet | 2025-06-01 | Low
|  | Host with the community, a history and heritage event in the Village Hall. | CM | Completed | 2025-06-08 | Medium |  | D-Day exhibition
|  | Investigate into the feasibility of re-publishing history book on parish 1952-53 and updating, with Heritage History grant. | Comms Off | Not started yet | 2025-06-01 | Low
We will team up with partners to promote more walking paths and trails, opening up access to the heritage of our parish.
|  | Compile an inventory of existing walks and trails | Comms Off | Not started yet | 2025-06-01 | Low
|  | Map of public footpaths in all notice boards with additional info | Comms Off | Not started yet | 2025-06-01 | Low
|  | Liaise with partners for developing walks and trails | Comms Off | Not started yet | 2025-06-01 | Low
|  | Produce maps for all existing walks | Comms Off | Not started yet | 2025-06-01 | Low
|  | Continue to support seasonal walks organised by the Women’s Institute | CM | Working on it | 2025-06-01 | Medium
|  | With community partners, develop at least one Heritage Trail in the Parish and an accompanying guide. | Comms Off | Not started yet | 2025-06-01 | Low
We will ensure that residents are aware on how to access and make a representation to the Listed Buildings Register and the Local list
|  | Review and publish the recorded Listed buildings in the Parish and from a walk-by survey, note any which look in poor condition or at risk and refer to Cheshire East Council. | Comms Off | Not started yet | 2025-06-01 | Low
|  | Review and publish list of buildings on the Local List. | Comms Off | Not started yet | 2025-06-01 | Low
We will use the planning process to ensure that new buildings respect the unique character of the parish. We will explore the advantages of implementing a Parish Design Guide.
|  | Use NP to comment on the suitability of new development design | Clerk | Working on it | 2025-06-01 | Medium |  | Ongoing via Planning Committee mainly
|  | Work with community partners at the time of the Neighbourhood Plan mid-term review, to assess the benefits and social value of developing a Parish Design Guide for the Parish to supplement the wider Cheshire East Guide. | Clerk | Completed | 2025-06-01 | Medium |  | Social value positive, but fund needed to complete the Parish Design Guide
We will care for the village War Memorial.
|  | Conduct a biannual cleaning schedule to ensure the War Memorial is in pristine condition year-round | Clerk | Working on it | 2025-06-01 | Medium
|  | Improve the accessibility pathway to the War Memorial to ensure it is wheelchair accessible by mid-term. | Clerk | Not started yet | 2025-06-01 | Low |  | Fund needed to progress with this action and at the moment they haven't been budgeted
|  | Ensure the War memorial is visible from the road at all times. Pruning or removal of some plants. | Clerk | Not started yet | 2025-06-01 | Low
Improving HEALTH AND WELLBEING
We will support and collaborate with initiatives that help locals lead healthier lives.
|  | Regularly promulgate advice from partners on staying healthy, through our communications channels. | Comms Off /CM | Working on it | 2025-06-01 | Low
|  | Continue to support Shakedown Wednesday school holiday only if funded | CM | Completed | 2024-05-23 |  |  | Fund have not been awarded toward the project
|  | Give priority to supporting and promoting events and clubs in the Parish which help physical, social and mental health and in the longer term look to facilitate in the Village Hall. | CM | Working on it | 2025-06-01 | Medium |  | Wellbeing Wednesday AM and PM sessions
To bring community together by leading or promoting which build social cohesion
|  | Host Community Places sessions in Village Hall. | CM | Completed | 2025-06-01 | Medium |  | Coffee garden sessions hosted at the VH as par of IMPACT
|  | Support Wellbeing Wednesday programme | CM | Working on it | 2025-06-01 | Medium
|  | Support IMPACT programme | CM | Completed | 2025-06-01 | Medium
|  | All events lead or oganised by the Community & Recreation Committee (such Christmas Carol, Remembrance Service,..) | CM | Working on it | 2025-06-01 | High
We will advocate for better access to health and social care services within our community, ensuring that everyone, especially at the local level, has the support they need.
|  | Act as a point of contact through our Information Gateway to direct residents to services | Comms Off (Clerk/CM) | Working on it | 2025-06-01 | Medium
|  | Contribute to the provision, recording and maintenance of defibrillators in the Parish, publicising the availability of grants | Clerk + Comms Off | Working on it | 2025-06-01 | Medium
|  | To promote Defibrillator Training sessions in Village Hall | CM | Completed | 2025-06-01 | Low |  | First Wellbeing Wednesday session May 2024
We will ensure that individuals with disabilities have their needs met by enhancing accessibility and providing adequate facilities.
|  | Have the marketing assets (e.g website, newsletter, signage,..) of the Parish Council professionally assessed for accessibility over the next 3 years | Comms Off | Not started yet | 2028-06-01 | Medium
|  | Have the physical assets (e.g Village Hall, Vine Tree, signage,..) of the Parish Council professionally assessed for accessibility over the next 5 years | Clerk | Not started yet | 2030-06-01 | Medium
We will oppose any new developments that result in the loss of recreational, green fields or sports facilities unless equivalent alternatives are provided.
|  | Through the planning process or consultations from developers. | Clerk | Working on it | 2025-06-01 | Medium |  | Via Planning Committee
|  | We will campaign for improved recreational or sports facilities throughout the parish, in accordance with development of the parish and NP | Clerk | Working on it | 2025-06-01 | Medium |  | Via Planning Committee
We will help local sports and leisure groups play a bigger part in meeting the community's needs.
|  | Liaise with sports and leisure organisations and look for opportunities to support through advice, facilitation, grants or lobbying. | Clerk | Completed | 2025-06-01 | Low |  | Via Wellbeing Wednesday
|  | Support and promote the development of new sports and leisure facilities to meet the needs of the local and surrounding population. | Clerk | Not started yet | 2025-06-01 | Low
|  | Recognise the needs of pedestrians and promote walking in the Parish. | CM | Working on it | 2025-06-01 | Medium |  | WI walk promote on newsletter
|  | Use planning system to include better facilities for cycling/walking in development proposals | Clerk | Working on it | 2025-06-01 | Medium |  | Via Planning Committee
We will maintain the Vine Tree Play area.
|  | Undertake regular safety checks and keep clean and tidy | Clerk | Working on it | 2025-06-01 | High
|  | Put together a 10 year plan to replace and improve the Vine Tree play area | Clerk | Not started yet | 2025-06-01 | Low
|  | Maintain boundary fences. | Clerk | Working on it | 2025-06-01 | High |  | Ground maintenance contract
|  | Have annual independent safety inspection. | Clerk | Working on it | 2025-06-01 | High |  | Done in July-September
We will provide allotments for residents
|  | Continue to provide a range of allotment services and to manage in accordance with our stated policy. | Clerk | Working on it | 2025-06-01 | High
|  | Undertake regular site inspections, to ensure that each site is being properly maintained and used. | Clerk | Working on it | 2025-06-01 | High
|  | Maintain boundary security at each site. | Clerk | Working on it | 2025-06-01 | Medium
We will collaborate with the Police and other partners to enhance community safety initiatives.
|  | Liaise with the Police concerning issues of crime or anti-social behaviour of particular concern to residents or businesses. | Clerk | Working on it | 2025-06-01 | High
|  | To disseminate information to help them stay safe via the Parish Council channels. | Comms Off (CM) | Working on it | 2025-06-01 | Medium
|  | Continue to fund a PCSO for as long as the role is supported by the council | Clerk | Working on it | 2025-06-01 | Medium
|  | Continue to publish information about the work of the PCSO in the Newsletter and on the Website. | Comms Off (CM) | Working on it | 2025-06-01 | Medium
|  | Ensure information is published weekly/fortnightly based on outcomes rather than day-to-day duties | Comms Off | Not started yet | 2025-06-01 | Low
|  | Ask PCSOto encourage safer and more considerable parking where footpath safety is compromised | Clerk | Working on it | 2025-06-01 | High
We will create a Parish Emergency Plan in collaboration with relevant external organisations.
|  | Liaise with the Emergency Planning Team at Cheshire Shared Services to ensure a local emergency plan cascades from the County Plan. | Clerk | Not started yet | 2025-06-01 | Low
|  | Identify potential community partners and ask for local volunteers. | Clerk | Not started yet | 2025-06-01 | Low
|  | Produce first draft of Emergency Plan to discuss with partners. | Clerk | Not started yet | 2025-12-31 | Low
|  | Publish final Emergency Plan. | Clerk | Not started yet | 2026-06-01 | Low
We will ensure that current home safety and health advice/information relevant to the Parish is accessible .
|  | Disseminate information on home and water safety through Parish Council channels. | Comms Off (CM) | Working on it | 2025-06-01 | Medium
|  | Disseminate information from Cheshire Fire and Rescue Service and support their campaigns. | Comms Off (CM) | Working on it | 2025-06-01 | Medium
|  | Share the latest information/advice from health providers and Police | Comms Off (CM) | Working on it | 2025-06-01 | Medium
We will conduct a thorough examination of the Council's activities and facilities to reduce crime.
|  | To comply with the Parish Council’s legal obligation by undertaking the audit across its range of functions and implementing recommendations. | Clerk | Not started yet | 2026-06-01 | High
We will advocate for better roads and regular maintenance, enhancing safety for all.
|  | Support the use of Speed Indication Devices and community speed watch. | Clerk | Working on it | 2025-06-01 | High
|  | Lobby the Police for mobile speed monitoring where necessary | Clerk | Completed | 2025-06-01 | High |  | ScG registered in the PCC SID program
|  | Use our influence to bring about speed limit reductions by lobbying Cheshire East Council and the Police, and through Planning and highways consultations. | Clerk | Working on it | 2025-06-01 | High |  | Ongoing provision of data to support speed review in Crewe Road, Gresty Road and Newcastle road
|  | Set up a Neighbourhood Watch for Potholes/street signs/road group to regulary report issue to highways | CM | Not started yet | 2025-06-01 | Low
PROTECTING THE ENVIRONMENT
We will collaborate with partners to safeguard and improve our local environment by preserving its natural beauty, biodiversity, and important landscapes.
|  | Review the Council’s Environmental and Sustainability Policy to ensure it fully addresses the goals in this Strategy. | Clerk | Not started yet | 2025-06-01 | Medium
|  | Seek to preserve and enhance the Parish’s biodiversity through supporting the retention, creation, and improvement of water and green infrastructure networks | Clerk | Working on it | 2025-06-01 | High |  | Acquisition of ecological mitigation area
|  | Enhancing the voluntary Watering Team | CM | Working on it | 2025-06-01 | Medium
|  | Continuing Building relationships with local businesses to encourage them to allocate Corporate Social Responsibilities days to best effect and with optimal outcomes in the Parish | CM | Working on it | 2025-06-01 | Medium
|  | Protect the Green Gap by challenging planning decisions that result in its loss, monitoring sites to ensure a gap remains, and through working with the local authority to enhance green gap provision, and by incorporating this into the neighbourhood plan | Clerk | Working on it | 2025-06-01 | High |  | Via Planning Committee
We will team up with partners to enhance our open spaces and green areas in the Parish.
|  | To work with partners to identify land which may be available for acquisition and potential uses. | Clerk | Not started yet | 2025-06-01 | Low |  | If opportunity arises
|  | To liaise with developers and Cheshire East Council through planning gain. | Clerk | Working on it | 2025-06-01 | Medium |  | Via planning committee and other channels
|  | To consider taking on additional open space from the local authority, if Cheshire East Council can’t maintain to an acceptable level. | Clerk | Not started yet | 2025-06-01 | Low |  | If opportunity arises
|  | Continuing to support volunteers who take on and develop green areas to enhance the local environment | Clerk/CM | Working on it | 2025-06-01 | Medium
We will ensure that public areas remain clean, easily accessible, and free of litter.
|  | Report major waste deposits to Cheshire East Council. | Clerk | Not started yet | 2025-06-01 | High |  | If opportunity arises
|  | Liaise with Cheshire East Council on joint working, assisting each other and waste disposal. | Clerk | Working on it | 2025-06-01 | Medium |  | Public consultation and public event attended
|  | Encourage residents to keep areas around their own homes/streets free of litter, weeds, .. Encourage residents to report Fly Tipping | Comms Off | Not started yet | 2025-06-01 | High
|  | Undertake a feasibility study into establishing a Ranger Service and define a potential role | Clerk | Not started yet | 2025-06-01 | High
|  | Organise clean-ups regularly, supporting volunteers with equipment, sacks, and disposal. | CM | Working on it | 2025-06-01 | Medium
|  | Continue to provide the Clean Team volunteers with the correct safety advice and insurance cover. | Clerk | Working on it | 2025-06-01 | High
We will maintain our gardens and flower displays. We will explore the possibility of taking on more responsibilities for grounds upkeep if the Cheshire East Council's budget cuts negatively affect our parish
|  | Ensure Grounds Maintenance Contract is in place, & operational with published standards. | Clerk | Completed | 2025-06-01 | High |  | Contract in plance
|  | Invite local organisations to help maintain flower beds/garden areas in return for advertising. | CM | Completed | 2025-06-01 | Medium |  | Scout, WI and residents
|  | Carry out regular monthly monitoring of Ground Maintenance Contract. | CM | Not started yet | 2025-06-01 | Medium
|  | Through contractors, maintain garden areas and floral displays for which the Council is responsible. | Clerk | Completed | 2025-06-01 | High |  | Contract in plance
|  | Undertake Spring Bulb Planting as part of IMPACT | CM | Completed | 2025-06-01 | Medium
|  | Complete Impact pollinator friendly projects. | CM | Completed | 2025-06-01 | Medium
|  | Maintain Telephone kiosk vertical gardens | CM | Working on it | 2025-06-01 | High
|  | Enlarge plant watering scheme | CM | Working on it | 2025-06-01 | Medium
We will actively acquire and support the development and maintenance of an ecological area.
|  | Complete the acquisition of the Western Ecological Area subject to a S106 agreement. | Clerk | Working on it | 2025-06-01 | High
|  | Draw up a development scheme and accompanying project plan. | Clerk | Working on it | 2025-06-01 | High
|  | Include routine maintenance in the Ground Maintenance Contract. | Clerk | Working on it | 2025-06-01 | High
|  | Campaign for provision of footpaths through and adjacent-to the area | Clerk | Working on it | 2025-06-01 | High
Work as part of the ChALC Net Zero efforts and identify initiatives that would benefit the Parish
|  | To join as member the ChALC Net Zero Working Group | Clerk | Completed | 2025-06-01 | Medium |  | Clerk joined the WG
We will serve as advocates and liaisons with other agencies to address and resolve issues within the parish
|  | Refer to CEC and other agencies through the Office Gateway | Clerk/Comms Off/CM | Working on it | 2025-06-01 | High
MAKING THE COUNCIL WORK BETTER
We will organise our work priorities based on a corporate strategy, after consulting with our communities and partners.
|  | Adopt corporate Strategy after consultation. | Clerk | Working on it | 2024-07-01 | High
|  | Adopt Delivery Plan for 2024-25 | Clerk | Working on it | 2024-07-01 | High
|  | Adopt Delivery Plan for 2025-26 | Clerk | Working on it | 2025-06-01 | High
We will enhance the skills and capabilities of the Council.
|  | Adopt a Training and Development Policy for Members and officers. | Clerk | Completed | 2025-06-01 | Medium
|  | Adopt annual Training Plan for 2024-5 | Clerk | Completed | 2025-06-01 | Medium |  | For officers
|  | Deliver Training Plan for 2024-5 | Clerk | Working on it | 2025-06-01 | High
|  | Review Staff requirements & structure to deliver Strategy | Clerk | Working on it | 2025-06-01 | High
|  | Recruit necessary staff for current year | Clerk | Not started yet | 2025-06-01 | High
|  | Recruit Remaining staff | Clerk | Not started yet | 2026-06-01 | Medium
|  | Adopt new/revised Job Descriptions/Person Specs. | Clerk | Completed | 2025-06-01 | Medium
|  | Implement any changes from Staffing Review for existing staff & issue revised contracts. | Clerk | Working on it | 2025-06-01 | High
|  | Review Employee Handbook and Employee appraisal scheme. | Clerk | Working on it | 2025-06-01 | High
|  | Complete Employee Development Reviews | Clerk | Not started yet | 2025-06-01 | High
|  | Remain eligible for the general power of competence. | Clerk | Completed | 2025-06-01 | High
We'll deliver excellent services either directly or through partnerships, tailored to meet both the needs of the community and individual preferences.
|  | Maintain an office at the Village Hall | Clerk | Completed | 2025-06-01 | High
|  | Consider accessibility issues as they arise and feasibility for improving accessibility at village hall. | Clerk | Working on it | 2025-06-01 | High
|  | Provide a full range of democratic and support services to Council, committees and individual members | Clerk | Working on it | 2025-06-01 | High |  | Ongoing
|  | Provide an Information gateway to other public bodies and voluntary organisations. | Clerk/Comms Off/CM | Working on it | 2025-06-01 | High
|  | Manage the Village Hall as a community asset, optimising occupancy & income. | Clerk | Working on it | 2025-06-01 | High |  | Ongoing
|  | Ensure the Village Hall is maintained to a high standard with areas identified to be included in the Village Hall budget. | Clerk | Working on it | 2025-06-01 | High |  | Ongoing
|  | Publish occupancy statistics for the Village Hall. | Clerk | Working on it | 2025-06-01 | High |  | published in the VH agena pack
|  | Undertake Village Hall Kitchen refurbishment project subject to grant approval. | Clerk | Completed | 2025-06-01 | Medium |  | Grant has been unsuccessful for the kitchen refuribishmen
|  | Review the utilisation of workspace in the Village Hall. | Clerk | Completed | 2025-06-01 | Medium |  | Downstairs lounge new meeting room
|  | Review the stated standards of Cheshire East Council’s Street Cleansing and Grounds maintenance services for the parish, whether this is being achieved and whether they are adequate. | Clerk | Not started yet | 2025-06-01 | Low
|  | Consider how services might be enhance to meet the needs of the Parish, consulting community partners as necessary. | Clerk | Not started yet | 2025-06-01 | Low |  | Up to member request
|  | To have tentative discussions with CEC on how these may be best supplemented, subject to avoiding double taxation and demonstrating community social value. | Clerk | Not started yet | 2025-06-01 | Low
|  | Continue contributions to Shavington Primary School to enable Parish/public use of Main Road/Primary School car park. | Clerk | Working on it | 2025-06-01 | High
|  | Look at the feasibility of taking on devolved services from the principal authority where not to do so would have an adverse effect on our Parish and it would meet social value criteria. | Clerk | Not started yet | 2025-06-01 | Low
We will implement a Delivery Plan focused on achieving outcomes, along with performance management to track progress.
|  | Adopt Performance Management Policy | Clerk | Not started yet | 2025-06-01 | Medium
|  | Report performance against Delivery Plan, Officer delegated decisions & non-implementation of resolutions every 2nd month | Clerk | Not started yet | 2025-06-01 | High
|  | Adopt a Quality Policy and set up staff “Quality Circles”. | Clerk | Not started yet | 2025-06-01 | Medium
|  | Implement Annual Improvement recommendations from Quality Circle | Clerk | Not started yet | 2025-06-01 | Medium
|  | Supplement Delivery Plan for major projects with a detailed Project Plan | Clerk | Not started yet | 2025-06-01 | Medium
Ensure proactive leadership and effective systems and checks to enhance the functioning of the Parish Council.
|  | Review committee TOR and include detailed delegation to committees and officers. | Clerk | Completed | 2025-06-01 | High
|  | Review Standing Orders & Financial Regs. | Clerk | Completed | 2025-06-01 | High
|  | We will set review dates against every policy and make sure these are adhered to | Clerk | Not started yet | 2025-06-01 | High
|  | Add additional governance and policy documents including Publication Scheme Information Guide and Pensions Discretions Policy | Clerk | Completed | 2025-06-01 | High
|  | Adopt Budget for 2025-26 | Clerk | Not started yet | 2025-06-01 | High
|  | Adopt Medium Term Financial Plan | Clerk | Working on it | 2025-06-01 | High
|  | Revise MTFP | Clerk | Not started yet | 2025-06-01 | High
|  | Finalise Accounts 2023-24 & approve AGAR | Clerk | Completed | 2025-06-01 | High
|  | Undertake VAT returns Quarterly & review VAT status | Clerk | Working on it | 2025-06-01 | High
|  | Monthly Financial Reports to Council/Committee | Clerk | Working on it | 2025-06-01 | High
|  | Continue all financial transactions in a timely manner in accordance with Financial Regulations | Clerk | Working on it | 2025-06-01 | High
|  | Undertake review of ear-marked reserves | Clerk | Working on it | 2025-06-01 | High
|  | Review and update Asset Register and expand information on major assets | Clerk | Working on it | 2025-06-01 | High |  | Ongoing
|  | Gain accreditation under the Local Council Award Scheme, Quality Level, Gold Level | Clerk | Not started yet | 2027-06-01 | Low
|  | Develop a range of quality based operating procedures: -Financial Procedures -Personnel Procedures -15 key procedures -All other procedures -Monitor compliance with operating procedures. | Clerk | Not started yet | 2026-06-01 | Low
|  | Complete all health and safety risk assessments for the year, including events. | Clerk | Working on it | 2025-06-01 | High
|  | Complete all statutory periodic safety inspections and checks. | Clerk | Working on it | 2025-06-01 | High
|  | Introduce regular safety toolbox talks/briefings to supplement formal safety training. | Clerk | Completed | 2025-06-01 | High
|  | Review Health and Safety Policy with Advisors | Clerk | Not started yet | 2026-06-01 | Low |  | Planned in 2025
|  | Undertake all business and financial risk assessments. | Clerk | Working on it | 2025-06-01 | High
|  | Review all business and financial risk assessments. | Clerk | Not started yet | 2026-06-01 | Low
We will ensure clear and open communication channels, fostering transparency in our actions.
|  | Undertake a review of the Council’s Information Technology and security, develop an implementation plan. And digital strategy. | Comms Off | Not started yet | 2025-06-01 | Medium
|  | Develop and adopt Communications and Marketing Policy. | Clerk | Completed | 2024-06-01 | High |  | Will need to be reviewed by the new Comms Off
|  | Continually improve the content of the Website, (including compliance with Transparency Regulations) social media posts and other channels of communication to make the Council more accessible and efficient. | Comms Off | Not started yet | 2025-06-01 | High
|  | Maintain and service all public noticeboards | Comms Off (CM) | Working on it | 2025-06-01 | Medium
|  | Produce an Annual Report for 2023-24 | CM | Completed | 2024-06-01 | High
|  | Continue to publish quarterly newsletters | CM | Working on it | 2024-06-01 | High
|  | Keep our Publication Scheme and Information Guide current and exceed “data transparency” requirements. | Clerk | Completed | 2024-06-01 | High
|  | Develop a suite of data protection policies | Clerk | Working on it | 2024-06-01 | High
|  | Maintain compliance with Data Protection and Freedom of Information requirements | Clerk | Completed | 2024-06-01 | High